## Sheet1
TASK | START DATE | END DATE | DURATION | RESPONSIBLE
Hardware Design | 3rd February 2019 | 9th February 2019 | 7 | All
PCB Design and build | 10th February 2019 | 16th February 2019 | 7 | Bella
Design and Build ofUI Mobile App | 13th February 2019 | 21st February 2019 | 9 | Bella
Integration with backend(Mobile) | 22nd February 2019 | 24th February 2019 | 3 | Bella
Mobile App Testing | 26th February 2019 | 28th February 2019 | 3 | Bella
Hardware Prototype for Identification | 1st March 2019 | 13th March 2019 | 12 | All
Prototype for Classification | 14th March 2019 | 24th March 2019 | 11 | All
Prototype Test | 31st March 2019 | 10th April 2019 | 11 | All
Integration with data from hardware | 11th April 2019 | 21st April 2019 | 11 | All
Actual Hardware build | 22nd April 2019 | 30th April 2019 | 9 | All
Entire System Test | 1st May 2019 | 20th May 2019 | 20 | All
Preparation for Project Defense | 22nd May 2019 | 25th May 2019 | 4 | All