## Sheet1
TASK | START DATE | END DATE | DURATION | RESPONSIBLE | STATUS | % COMPLETE
Hardware Design | 3rd February 2019 | 9th February 2019 | 7 | All | In progress | 85%
PCB Design and build | 10th February 2019 | 16th February 2019 | 7 | Bella | In progress
Design and Build ofUI Mobile App | 13th February 2019 | 21st February 2019 | 9 | Bella | In progress
Integration with backend(Mobile) | 22nd February 2019 | 24th February 2019 | 3 | Bella | Not started | 0%
Mobile App Testing | 26th February 2019 | 28th February 2019 | 3 | Bella | Not started | 0%
Hardware Prototype for Identification | 1st March 2019 | 13th March 2019 | 12 | All | Not started | 0%
Prototype for Classification | 14th March 2019 | 24th March 2019 | 11 | All | Not started | 0%
Prototype Test | 31st March 2019 | 10th April 2019 | 11 | All | Not started | 0%
Integration with data from hardware | 11th April 2019 | 17th April 2019 | 7 | All | Not started | 0%
Prototype Test 2 | 18th April 2019 | 21st April 2019 | 4 | All | Not started | 0%
Actual Hardware build | 22nd April 2019 | 30th April 2019 | 9 | All | Not started | 0%
Entire System Test | 1st May 2019 | 20th May 2019 | 20 | All | Not started | 0%
Preparation for Project Defense | 22nd May 2019 | 25th May 2019 | 4 | All | Not started | 0%
STATUS AVAILABLE
Complete
Not started
In progress
Overdue